## Overview
UAT WORKBOOK · LMS COMPLETIONS
Halvorsen Freight
Learning Platform → SuccessFactors LMS · UAT · generated 2026-10-09
✗ NOT READY FOR CUSTOMER UAT · 2 blocking checks
BLOCKING CHECKS | TEST CASES | PASSED | OPEN ISSUES
2 | 9 | 0 | 0
must be 0 before UAT starts | 3 core · 6 edge | 0 failed · 0 blocked | on the Issue Log
TEST PROGRESS
░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░ |  |  |  | 0% run
✓ 0 passed ✗ 0 failed ⚠ 0 blocked ○ 9 not run
DETAILS
Workflow | Halvorsen Freight ¦ Learning Platform -> SuccessFactors LMS ¦ Completions
Workflow ID | wf_8b21de04-hf-completions
Schedule (as built) | daily
Match key | STUDENT_ID + ITEM_ID + COMPLETION_DATE
Spec signed by | Priya Natarajan, LMS Administrator, Halvorsen Freight (2026-09-29)
HOW TO USE THIS WORKBOOK
1 Pre-UAT Validation | Integration team fixes every ✗ FAIL before the customer starts testing.
2 Field Mappings | Customer checks each field against a real record and marks it ✓ Verified.
3 Test Cases | Run each case with its persona from Test Data; record the result and status.
4 Issue Log | Log every failed or blocked case and link the Issue ID back to the test case.
5 Sign-off | When every criterion reads ✓ Met, both sides sign and cutover is scheduled.
Yellow cells are inputs. Everything else is generated or calculated.

## Pre-UAT Validation
Pre-UAT Validation
Halvorsen Freight · LMS Completions · the workflow as built vs. the signed requirements spec
Resolve every ✗ FAIL before the customer starts testing. When a fix ships, re-run the generator (check IDs stay the same) or set Result and note it in Resolution.
Check | Category | Signed requirement | Workflow as built | Result | Severity | Recommended action | Resolution
V-11 | Dates & time zones | COMPLETION_DATE converted in America/Chicago | Converted in UTC | ✗ FAIL | High | Set timezone to America/Chicago. Late-evening completions will otherwise land on the next calendar day in the customer's system.
V-12 | Error handling | Retry on HTTP 429, 500, 503 | Retries on 500, 502, 503 | ✗ FAIL | High | Add retry on 429. 429 = API rate limit; large first loads will drop records without it.
V-01 | Scope | Integration type: lms_completions | Workflow tagged: lms_completions | ✓ PASS | — | —
V-02 | Identity | Records match on learner.external_id → STUDENT_ID | Match on STUDENT_ID; STUDENT_ID ← learner.external_id | ✓ PASS | — | —
V-03 | Field mapping | STUDENT_ID ← learner.external_id | STUDENT_ID ← learner.external_id | ✓ PASS | — | —
V-04 | Field mapping | ITEM_ID ← course.external_course_id | ITEM_ID ← course.external_course_id | ✓ PASS | — | —
V-05 | Field mapping | ITEM_TYPE ← course.course_type | ITEM_TYPE ← course.course_type | ✓ PASS | — | —
V-06 | Field mapping | COMPLETION_DATE ← completed_at | COMPLETION_DATE ← completed_at | ✓ PASS | — | —
V-07 | Field mapping | COMPLETION_STATUS ← status | COMPLETION_STATUS ← status | ✓ PASS | — | —
V-08 | Field mapping | SCORE ← score | SCORE ← score | ✓ PASS | — | —
V-09 | Population filter | course_type in OLT | course_type in OLT | ✓ PASS | — | —
V-10 | Schedule | Runs daily | Runs daily | ✓ PASS | — | —

## Field Mappings
Field Mappings
Every field written to SuccessFactors LMS, plus agreed fields not yet built
Customer: check each field against one real record and set Verified. Sample values come from persona P-02 on Test Data.
# | Source field (Learning Platform) | Target field (SuccessFactors LMS) | Agreed source (spec) | Transform | Sample value | Flag | Verified | Notes
1 | learner.external_id | STUDENT_ID | learner.external_id | — | HF-12871
2 | course.external_course_id | ITEM_ID | course.external_course_id | — | COMP-220
3 | course.course_type | ITEM_TYPE | course.course_type | constant:OLT | OLT
4 | completed_at | COMPLETION_DATE | completed_at | datetime:epoch_ms (tz UTC) | 2026-10-08 23:41 | ✗ V-11
5 | status | COMPLETION_STATUS | status | value_map: completed→OLT-COMPLETE | completed
6 | score | SCORE | score | — | 88

## Test Cases
Test Cases
Halvorsen Freight · LMS Completions · Learning Platform → SuccessFactors LMS
Yellow cells are for the tester. Set Status from the dropdown; log every ✗ Fail or ⚠ Blocked in the Issue Log and put its ID here.
TC ID | Scenario | Type | Test data | Preconditions | Steps | Expected result | Actual result | Status | Tester | Date | Issue ID | Pre-UAT dependency
TC-01 | Completion posts to learning history | Core | P-01 | P-01 exists as a student in the LMS; SAFE-101 exists in the LMS catalog as OLT. | 1. P-01 completes SAFE-101 in the learning platform. 2. Run the completions sync (or wait for the next scheduled run). 3. Open P-01's learning history in SuccessFactors LMS. | One completion record for SAFE-101 with correct date, status and score. |  | ○ Not run
TC-02 | All mapped fields land correctly | Core | P-01 | Completion from the previous case has posted. | Compare each field on the Field Mappings tab against the LMS record. | Every field matches; mark each row Verified on the Field Mappings tab. |  | ○ Not run |  |  |  | ⚠ Will fail until V-11 is fixed
TC-03 | Late-evening completion keeps its calendar date | Edge | P-02 | P-02 completes at 11:41 PM local time. | 1. P-02 completes COMP-220 at 23:41 America/Chicago. 2. Run the completions sync (or wait for the next scheduled run). 3. Check COMPLETION_DATE in SuccessFactors LMS. | Completion date shows 2026-10-08, not 2026-10-09. |  | ○ Not run |  |  |  | ⚠ Will fail until V-11 is fixed
TC-04 | Non-OLT course is not sent | Edge | P-03 | ILT-040 is an instructor-led course. | 1. Mark P-03 complete on ILT-040. 2. Run the completions sync (or wait for the next scheduled run). | No learning-history record is posted for ILT-040. Not logged as an error. |  | ○ Not run
TC-05 | Learner with no matching LMS student | Edge | P-04 | HF-20417 is a new hire not yet provisioned in the LMS. | 1. P-04 completes SAFE-101. 2. Run the completions sync (or wait for the next scheduled run). 3. Check the integration error log. | Record is logged as 'student not found' and retried on the next run; no phantom student is created. |  | ○ Not run
TC-06 | Duplicate completion is idempotent | Edge | P-05 | P-05's completion already posted. | 1. Re-run the sync for the same window. 2. Check P-05's history in SuccessFactors LMS. | Still exactly one record for that completion date. |  | ○ Not run
TC-07 | Retake on a later date | Edge | P-06 | P-06 is the same learner as P-05, retaking SAFE-101 the next day. | 1. Learner completes SAFE-101 again on 2026-10-09. 2. Run the completions sync (or wait for the next scheduled run). | A second history record posts with the new date and score; the first is unchanged. |  | ○ Not run
TC-08 | Course not in LMS catalog | Edge | P-07 | NEW-999 has no matching ITEM_ID in the LMS. | 1. P-07 completes NEW-999. 2. Run the completions sync (or wait for the next scheduled run). 3. Check the error log. | Record is rejected with a readable 'item not found' reason; batch continues. |  | ○ Not run
TC-09 | Peak-volume batch completes | Core | — | Bulk-complete 2500 records in the test tenant (e.g. a compliance deadline). | 1. Trigger a bulk completion batch. 2. Run the completions sync (or wait for the next scheduled run). 3. Reconcile counts: platform completions vs LMS records. | All records post. Rate-limit (HTTP 429) responses are retried, not dropped. |  | ○ Not run |  |  |  | ⚠ Will fail until V-12 is fixed

## Test Data
Test Data
Fictional personas the test cases use
Create or modify these records in the TEST tenant only. Times are the customer's local time zone.
Persona | Scenario | learner.external_id | Learner name | course.external_course_id | Course title | course.course_type | completed_at | status | score
P-01 | Standard completion | HF-11802 | Devon Akintola | SAFE-101 | Forklift Safety Refresher | OLT | 2026-10-08 14:22 | completed | 92
P-02 | Late-evening completion | HF-12871 | Samir Haddad | COMP-220 | Anti-Bribery Essentials | OLT | 2026-10-08 23:41 | completed | 88
P-03 | Non-OLT course | HF-15560 | Jordan Whitaker-Lee | ILT-040 | Manager Workshop (in person) | ILT | 2026-10-07 16:05 | completed
P-04 | No matching LMS student | HF-20417 | Renata Alcott | SAFE-101 | Forklift Safety Refresher | OLT | 2026-10-08 09:10 | completed | 100
P-05 | Duplicate completion | HF-13002 | Aisha Rahman | SAFE-101 | Forklift Safety Refresher | OLT | 2026-10-08 10:30 | completed | 95
P-06 | Retake on a later date | HF-13002 | Aisha Rahman | SAFE-101 | Forklift Safety Refresher | OLT | 2026-10-09 08:15 | completed | 98
P-07 | Course missing from LMS catalog | HF-17788 | Zoë Ó Briain-Søndergaard | NEW-999 | Pilot Course (not in catalog) | OLT | 2026-10-08 11:00 | completed | 75

## Issue Log
Issue Log
Every failed or blocked test case gets a row here
Row 7 is a greyed-out example showing the format; it is not counted. Log issues from row 8.
Issue ID | TC ID | Severity | Description | Owner | Opened | Status | Resolution | Closed
ISS-000 | TC-06 | High | Rehired worker created as a new user instead of reactivating the original. | Integration team | 2026-10-09 | Example | Hire date source corrected; re-tested OK. | 2026-10-09
ISS-001
ISS-002
ISS-003
ISS-004
ISS-005
ISS-006
ISS-007
ISS-008
ISS-009
ISS-010
ISS-011
ISS-012
ISS-013
ISS-014
ISS-015
ISS-016
ISS-017
ISS-018
ISS-019
ISS-020
ISS-021
ISS-022
ISS-023
ISS-024
ISS-025
ISS-026
ISS-027
ISS-028
ISS-029
ISS-030

## Sign-off
UAT Sign-off
Halvorsen Freight · LMS Completions
Criteria are formulas and update as the workbook is filled in. Sign only when every criterion reads ✓ Met.
Criterion | Status
No failing pre-UAT checks | ✗ Not met
Every Core test case passed | ✗ Not met
Every Edge test case run, nothing blocked | ✗ Not met
No open High-severity issues | ✓ Met
Every field mapping verified | ✗ Not met
APPROVALS
Name | Role | Signature | Date
Priya Natarajan | LMS Administrator, Halvorsen Freight
Integration Engineer

## AI Instructions
AI Instructions
For Claude (or any agent) maintaining this workbook. Humans can skip this tab.
Topic | Instruction
Source of truth | The workflow export and the signed requirements spec. Never invent fields, values or customer decisions.
Regenerating | When the workflow changes, re-run generate_uat.py with the new export. Check IDs are stable between runs. Carry over Actual result, Status, Tester, Date and Issue ID by matching on Scenario, not TC ID.
Validation | A ✗ FAIL on Pre-UAT Validation blocks customer testing. Summarise each FAIL in plain language with the fix, ordered by severity. ⚠ WARN and ℹ INFO items need a customer decision, not a silent fix.
Test cases | Add a case only when the workflow or spec introduces a behaviour not already covered. Each case needs a persona from Test Data, numbered steps and one observable expected result.
Test data | All personas are fictional and live in the TEST tenant. Never copy production records into this workbook.
Tone | Customer-facing. Short sentences, no internal jargon, no blame. Name systems the way the customer does.
Sign-off | Do not type ✓ Met by hand. Criteria are formulas; fix the underlying data instead.