## Overview
UAT WORKBOOK · HRIS USER SYNC
Halvorsen Freight
Workday → Learning Platform · UAT · generated 2026-10-09
✗ NOT READY FOR CUSTOMER UAT · 3 blocking checks
BLOCKING CHECKS | TEST CASES | PASSED | OPEN ISSUES
3 | 16 | 0 | 0
must be 0 before UAT starts | 4 core · 12 edge | 0 failed · 0 blocked | on the Issue Log
TEST PROGRESS
░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░ |  |  |  | 0% run
✓ 0 passed ✗ 0 failed ⚠ 0 blocked ○ 16 not run
DETAILS
Workflow | Halvorsen Freight ¦ Workday -> Learning Platform ¦ User Sync
Workflow ID | wf_3f9c1a72-hf-users
Schedule (as built) | every 15 minutes
Match key | external_id
Spec signed by | Dana Whitfield, HRIS Manager, Halvorsen Freight (2026-09-28) Marcus Oyelaran, IT Integration Lead, Halvorsen Freight (2026-09-29)
HOW TO USE THIS WORKBOOK
1 Pre-UAT Validation | Integration team fixes every ✗ FAIL before the customer starts testing.
2 Field Mappings | Customer checks each field against a real record and marks it ✓ Verified.
3 Test Cases | Run each case with its persona from Test Data; record the result and status.
4 Issue Log | Log every failed or blocked case and link the Issue ID back to the test case.
5 Sign-off | When every criterion reads ✓ Met, both sides sign and cutover is scheduled.
Yellow cells are inputs. Everything else is generated or calculated.

## Pre-UAT Validation
Pre-UAT Validation
Halvorsen Freight · HRIS User Sync · the workflow as built vs. the signed requirements spec
Resolve every ✗ FAIL before the customer starts testing. When a fix ships, re-run the generator (check IDs stay the same) or set Result and note it in Resolution.
Check | Category | Signed requirement | Workflow as built | Result | Severity | Recommended action | Resolution
V-07 | Field mapping | hire_date ← Hire_Date (Most recent hire date so rehires get onboarding content) | hire_date ← Original_Hire_Date | ✗ FAIL | High | Change source from Original_Hire_Date to Hire_Date.
V-12 | Field mapping | manager_email ← Manager_Email (Drives manager nudges and team reporting) | Not mapped | ✗ FAIL | High | Add mapping Manager_Email → manager_email in the data mapper.
V-15 | Population filter | Employee_Class not_in CONTRACTOR, INTERN, SEASONAL | Employee_Class not_in CONTRACTOR, INTERN | ✗ FAIL | High | Missing value(s): SEASONAL. Update the filter to match the signed spec.
V-16 | Schedule | Runs daily | Runs every 15 minutes | ⚠ WARN | Medium | Faster cadence is fine for UAT. Revert to daily before production cutover.
V-14 | Field mapping | Not in signed spec | cost_center ← Cost_Center | ℹ INFO | Low | Confirm with the customer that this field should sync, or remove it.
V-01 | Scope | Integration type: hris_user_sync | Workflow tagged: hris_user_sync | ✓ PASS | — | —
V-02 | Identity | Records match on Employee_ID → external_id | Match on external_id; external_id ← Employee_ID | ✓ PASS | — | —
V-03 | Field mapping | external_id ← Employee_ID | external_id ← Employee_ID | ✓ PASS | — | —
V-04 | Field mapping | email ← Work_Email | email ← Work_Email | ✓ PASS | — | —
V-05 | Field mapping | first_name ← Preferred_First_Name | first_name ← Preferred_First_Name | ✓ PASS | — | —
V-06 | Field mapping | last_name ← Last_Name | last_name ← Last_Name | ✓ PASS | — | —
V-08 | Field mapping | status ← Worker_Status | status ← Worker_Status | ✓ PASS | — | —
V-09 | Field mapping | department ← Department | department ← Department | ✓ PASS | — | —
V-10 | Field mapping | job_title ← Job_Title | job_title ← Job_Title | ✓ PASS | — | —
V-11 | Field mapping | location ← Work_Location | location ← Work_Location | ✓ PASS | — | —
V-13 | Field mapping | employee_class ← Employee_Class | employee_class ← Employee_Class | ✓ PASS | — | —
V-17 | Lifecycle | Status 'Active' → active | Status 'Active' → active | ✓ PASS | — | —
V-18 | Lifecycle | Status 'On Leave' → active | Status 'On Leave' → active | ✓ PASS | — | —
V-19 | Lifecycle | Status 'Terminated' → inactive | Status 'Terminated' → inactive | ✓ PASS | — | —
V-20 | Lifecycle | Worker missing from feed → deactivate | Worker missing from feed → deactivate | ✓ PASS | — | —
V-21 | Error handling | Retry on HTTP 429, 500, 503 | Retries on 429, 500, 503 | ✓ PASS | — | —

## Field Mappings
Field Mappings
Every field written to Learning Platform, plus agreed fields not yet built
Customer: check each field against one real record and set Verified. Sample values come from persona P-02 on Test Data.
# | Source field (Workday) | Target field (Learning Platform) | Agreed source (spec) | Transform | Sample value | Flag | Verified | Notes
1 | Employee_ID | external_id | Employee_ID | — | HF-11802
2 | Work_Email | email | Work_Email | lowercase | devon.akintola@halvorsenfreight.example
3 | Preferred_First_Name | first_name | Preferred_First_Name | — | Devon
4 | Last_Name | last_name | Last_Name | — | Akintola
5 | Original_Hire_Date | hire_date | Hire_Date | date:YYYY-MM-DD | 2019-03-04 | ✗ V-07
6 | Worker_Status | status | Worker_Status | value_map: Active→active, On Leave→active, Terminated→inactive | Active
7 | Department | department | Department | — | Fleet Maintenance
8 | Job_Title | job_title | Job_Title | — | Diesel Technician II
9 | Work_Location | location | Work_Location | — | Gary, IN
10 | Employee_Class | employee_class | Employee_Class | — | FULL_TIME
11 | Cost_Center | cost_center | — not in spec — | — |  | ℹ V-14
12 | — not built — | manager_email | Manager_Email | — | lena.kovacs@halvorsenfreight.example | ✗ V-12

## Test Cases
Test Cases
Halvorsen Freight · HRIS User Sync · Workday → Learning Platform
Yellow cells are for the tester. Set Status from the dropdown; log every ✗ Fail or ⚠ Blocked in the Issue Log and put its ID here.
TC ID | Scenario | Type | Test data | Preconditions | Steps | Expected result | Actual result | Status | Tester | Date | Issue ID | Pre-UAT dependency
TC-01 | New hire is created | Core | P-01 | P-01 exists in Workday with a future-dated or current hire date; not yet in Learning Platform. | 1. Confirm P-01 is in the source report. 2. Run the sync (or wait for the next scheduled run). 3. Search Learning Platform for external_id HF-20417. | User created with external_id, email, name and every mapped field populated (check against Field Mappings tab). |  | ○ Not run
TC-02 | All mapped fields populate correctly | Core | P-02 | P-02 already active in both systems. | 1. Export P-02's record from Workday. 2. Open the user in Learning Platform. 3. Compare each field listed on the Field Mappings tab. | Every field matches the source value after transforms; mark each row Verified on the Field Mappings tab. |  | ○ Not run |  |  |  | ⚠ Will fail until V-07, V-12 are fixed
TC-03 | Attribute update propagates | Core | P-02 | P-02 active and synced. | 1. In Workday, change P-02's Job_Title to 'Diesel Technician III'. 2. Run the sync (or wait for the next scheduled run). 3. Check the user in Learning Platform. | Job title updates on the existing user. No duplicate user is created. |  | ○ Not run
TC-04 | Termination deactivates the user | Edge | P-03 | P-03 active in both systems. | 1. Terminate P-03 in Workday (effective today). 2. Run the sync (or wait for the next scheduled run). 3. Check P-03 in Learning Platform. | User is set to inactive and stops receiving content. Completion history is retained. |  | ○ Not run
TC-05 | Leave of absence keeps the user active | Edge | P-05 | P-05 active in both systems. | 1. Place P-05 on leave in Workday. 2. Run the sync (or wait for the next scheduled run). 3. Check P-05 in Learning Platform. | User remains active (per signed spec). Status field reflects leave if exposed. |  | ○ Not run
TC-06 | Rehire reactivates the original user | Edge | P-04 | P-04 was terminated in 2024 and has an inactive user in the target. Rehired 2026-10-05 under the same Employee_ID. | 1. Confirm P-04 shows Hire_Date 2026-10-05 and Original_Hire_Date 2017-08-21 in Workday. 2. Run the sync (or wait for the next scheduled run). 3. Check P-04 in Learning Platform. | Existing user is reactivated (no duplicate) and hire_date = 2026-10-05 so new-hire content is assigned. |  | ○ Not run |  |  |  | ⚠ Will fail until V-07 is fixed
TC-07 | Email change updates, does not duplicate | Edge | P-06 | P-06 active and synced with jordan.whitaker-lee@…. | 1. Change P-06's Work_Email to jordan.lee@halvorsenfreight.example in Workday. 2. Run the sync (or wait for the next scheduled run). 3. Search Learning Platform by external_id HF-15560. | Same user now shows the new email. No second account. SSO login still works. |  | ○ Not run
TC-08 | Name change propagates | Edge | P-06 | P-06 active and synced. | 1. Change P-06's Last_Name to 'Lee' in Workday. 2. Run the sync (or wait for the next scheduled run). | Last name updates on the existing user; display name refreshes in reports. |  | ○ Not run
TC-09 | Excluded class (contractor) is not created | Edge | P-07 | P-07 has Employee_Class = CONTRACTOR. | 1. Confirm P-07 appears in the source report. 2. Run the sync (or wait for the next scheduled run). 3. Search Learning Platform for P-07's Employee_ID. | No user is created. The record is skipped by the population filter. |  | ○ Not run
TC-10 | Excluded class (seasonal) is not created | Edge | P-08 | P-08 has Employee_Class = SEASONAL. | 1. Confirm P-08 appears in the source report. 2. Run the sync (or wait for the next scheduled run). 3. Search Learning Platform for P-08's Employee_ID. | No user is created. The record is skipped by the population filter. |  | ○ Not run |  |  |  | ⚠ Will fail until V-15 is fixed
TC-11 | Duplicate email across two workers | Edge | P-09 / P-10 | P-09 and P-10 share chris.nguyen@… with different Employee_IDs. | 1. Run the sync (or wait for the next scheduled run). 2. Check the error log and both Employee_IDs in Learning Platform. | Records are NOT merged. Second record is rejected and logged for HRIS cleanup; first user unaffected. |  | ○ Not run
TC-12 | Special characters are preserved | Edge | P-11 | P-11 has diacritics and a hyphenated surname. | 1. Run the sync (or wait for the next scheduled run). 2. Open P-11 in Learning Platform and in a report export. | Name displays exactly as in source (Zoë Ó Briain-Søndergaard) in UI and CSV export. |  | ○ Not run
TC-13 | Record missing a required field is rejected cleanly | Edge | P-12 | P-12 has no Work_Email. | 1. Run the sync (or wait for the next scheduled run). 2. Check the integration error log. | Record is skipped and logged with a readable reason. The rest of the batch completes. |  | ○ Not run
TC-14 | Manager change updates reporting line | Edge | P-13 | P-13 synced with manager lena.kovacs@…. | 1. Change P-13's manager in Workday to tomas.berg@…. 2. Run the sync (or wait for the next scheduled run). 3. Check P-13's manager in Learning Platform. | manager_email updates; P-13 moves to the new manager's team view. |  | ○ Not run |  |  |  | ⚠ Will fail until V-12 is fixed
TC-15 | Worker who drops off the feed | Edge | P-03 | A terminated worker ages out of the report window (include_terminated_days). | 1. Remove P-03 from the source report (or wait past the window). 2. Run the sync (or wait for the next scheduled run). | User is handled per spec: deactivate. No error is raised. |  | ○ Not run
TC-16 | Full-population reconciliation | Core | — | First full run in the test tenant. | 1. Count workers in the source report. 2. Subtract excluded classes. 3. Compare to active users in Learning Platform. | Counts reconcile exactly. Any difference is explained in the Issue Log. |  | ○ Not run

## Test Data
Test Data
Fictional personas the test cases use
Create or modify these records in the TEST tenant only. Times are the customer's local time zone.
Persona | Scenario | Employee_ID | Preferred_First_Name | Last_Name | Work_Email | Employee_Class | Worker_Status | Hire_Date | Original_Hire_Date | Department | Job_Title | Work_Location | Manager_Email
P-01 | New hire | HF-20417 | Renata | Alcott | renata.alcott@halvorsenfreight.example | FULL_TIME | Active | 2026-10-12 | 2026-10-12 | Operations | Dispatch Coordinator | Joliet, IL | tomas.berg@halvorsenfreight.example
P-02 | Existing active worker | HF-11802 | Devon | Akintola | devon.akintola@halvorsenfreight.example | FULL_TIME | Active | 2019-03-04 | 2019-03-04 | Fleet Maintenance | Diesel Technician II | Gary, IN | lena.kovacs@halvorsenfreight.example
P-03 | Termination | HF-14455 | Graham | Pell | graham.pell@halvorsenfreight.example | FULL_TIME | Terminated | 2021-06-14 | 2021-06-14 | Sales | Account Executive | Chicago, IL | maya.shah@halvorsenfreight.example
P-04 | Rehire | HF-09310 | Lucia | Ferreira | lucia.ferreira@halvorsenfreight.example | FULL_TIME | Active | 2026-10-05 | 2017-08-21 | Warehouse | Shift Lead | Joliet, IL | tomas.berg@halvorsenfreight.example
P-05 | Leave of absence | HF-12871 | Samir | Haddad | samir.haddad@halvorsenfreight.example | FULL_TIME | On Leave | 2020-01-13 | 2020-01-13 | Finance | AP Specialist | Chicago, IL | maya.shah@halvorsenfreight.example
P-06 | Email / name change | HF-15560 | Jordan | Whitaker-Lee | jordan.whitaker-lee@halvorsenfreight.example | FULL_TIME | Active | 2022-02-07 | 2022-02-07 | HR | HR Business Partner | Chicago, IL | maya.shah@halvorsenfreight.example
P-07 | Excluded class (contractor) | HF-C0381 | Ines | Moreau | ines.moreau@halvorsenfreight.example | CONTRACTOR | Active | 2026-09-01 | 2026-09-01 | IT | Network Consultant | Remote | lena.kovacs@halvorsenfreight.example
P-08 | Excluded class (seasonal) | HF-S1142 | Kwame | Boateng | kwame.boateng@halvorsenfreight.example | SEASONAL | Active | 2026-10-01 | 2026-10-01 | Warehouse | Seasonal Loader | Gary, IN | tomas.berg@halvorsenfreight.example
P-09 | Duplicate email | HF-16023 | Chris | Nguyen | chris.nguyen@halvorsenfreight.example | FULL_TIME | Active | 2023-05-15 | 2023-05-15 | Operations | Route Planner | Joliet, IL | tomas.berg@halvorsenfreight.example
P-10 | Duplicate email (2nd record) | HF-16024 | Christine | Nguyen | chris.nguyen@halvorsenfreight.example | PART_TIME | Active | 2026-09-22 | 2026-09-22 | Customer Service | CS Representative | Remote | maya.shah@halvorsenfreight.example
P-11 | Special characters | HF-17788 | Zoë | Ó Briain-Søndergaard | zoe.obriain@halvorsenfreight.example | FULL_TIME | Active | 2024-11-04 | 2024-11-04 | Legal | Contracts Manager | Chicago, IL | maya.shah@halvorsenfreight.example
P-12 | Missing required field | HF-18120 | Pat | Delgado |  | FULL_TIME | Active | 2026-10-06 | 2026-10-06 | Warehouse | Forklift Operator | Gary, IN | tomas.berg@halvorsenfreight.example
P-13 | Manager change | HF-13002 | Aisha | Rahman | aisha.rahman@halvorsenfreight.example | FULL_TIME | Active | 2018-09-10 | 2018-09-10 | Operations | Terminal Manager | Joliet, IL | lena.kovacs@halvorsenfreight.example

## Issue Log
Issue Log
Every failed or blocked test case gets a row here
Row 7 is a greyed-out example showing the format; it is not counted. Log issues from row 8.
Issue ID | TC ID | Severity | Description | Owner | Opened | Status | Resolution | Closed
ISS-000 | TC-06 | High | Rehired worker created as a new user instead of reactivating the original. | Integration team | 2026-10-09 | Example | Hire date source corrected; re-tested OK. | 2026-10-09
ISS-001
ISS-002
ISS-003
ISS-004
ISS-005
ISS-006
ISS-007
ISS-008
ISS-009
ISS-010
ISS-011
ISS-012
ISS-013
ISS-014
ISS-015
ISS-016
ISS-017
ISS-018
ISS-019
ISS-020
ISS-021
ISS-022
ISS-023
ISS-024
ISS-025
ISS-026
ISS-027
ISS-028
ISS-029
ISS-030

## Sign-off
UAT Sign-off
Halvorsen Freight · HRIS User Sync
Criteria are formulas and update as the workbook is filled in. Sign only when every criterion reads ✓ Met.
Criterion | Status
No failing pre-UAT checks | ✗ Not met
Every Core test case passed | ✗ Not met
Every Edge test case run, nothing blocked | ✗ Not met
No open High-severity issues | ✓ Met
Every field mapping verified | ✗ Not met
APPROVALS
Name | Role | Signature | Date
Dana Whitfield | HRIS Manager, Halvorsen Freight
Marcus Oyelaran | IT Integration Lead, Halvorsen Freight
Integration Engineer

## AI Instructions
AI Instructions
For Claude (or any agent) maintaining this workbook. Humans can skip this tab.
Topic | Instruction
Source of truth | The workflow export and the signed requirements spec. Never invent fields, values or customer decisions.
Regenerating | When the workflow changes, re-run generate_uat.py with the new export. Check IDs are stable between runs. Carry over Actual result, Status, Tester, Date and Issue ID by matching on Scenario, not TC ID.
Validation | A ✗ FAIL on Pre-UAT Validation blocks customer testing. Summarise each FAIL in plain language with the fix, ordered by severity. ⚠ WARN and ℹ INFO items need a customer decision, not a silent fix.
Test cases | Add a case only when the workflow or spec introduces a behaviour not already covered. Each case needs a persona from Test Data, numbered steps and one observable expected result.
Test data | All personas are fictional and live in the TEST tenant. Never copy production records into this workbook.
Tone | Customer-facing. Short sentences, no internal jargon, no blame. Name systems the way the customer does.
Sign-off | Do not type ✓ Met by hand. Criteria are formulas; fix the underlying data instead.